## Dashboard
OVERALL
Overall Health of Project |  |  |  |  | Total # of Goals | Total Goals in Progress | Total Goals Not Started | Total Goals Complete |  | Project Highlights
[5 empty] | 8 | 8 | 0 | 0 |  | Goal 4: Aviation Education, We have continued partnerships with schools for the 2026 and 2027 school year. Goal 5: Environmental Issues: Completed Noise Round Table on September 16th.
|  |  |  | Total # of Objectives | Total Objectives in Progress | Total Objectives Not Started | Total Objectives Complete | Total Objectives - ON TIME | Total Objectives - LATE
|  |  |  | 30 | 25 | 0 | 5 | 30 | 0
STATUS
| Project Progress |  |  |  | Goal 1: Increasing Profitability | Goal 2: Improve Collaboration | Goal 3: Regional Transportation | Goal 4: Aviation Education
[5 empty] | 0% | 25% | 0% | 40%
[10 empty] | Not Started | 28
[10 empty] | In Progress | 43
[5 empty] | Goal 5: Environmental Issues | Goal 6: Emerging Technologies | Goal 7: Increase Operations | Goal 8: Fuel Purchases Programs |  | Complete | 22
[5 empty] | 66.67% | 0% | 0% | 0%
Complete | 0 | Complete | 5
In Progress | 8 | In Progress | 25
Not Started | 0 | Not Started | 0
|  | On time | 30
|  | Late | 0
Pie Chart
Bar Char
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Goal 1
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | O:On-time | O:Late | G-C (Y/N)
[7 empty] | 0 | 4 | 0 | 4 | 0 | No
[7 empty] | T-NS | T-IP | T-C | T:On-time | 1 | 0
GOAL 1: | Pursue & Implement Opportunities for Increasing Profitability to Promote Economic Stability | [5 empty] | 4 | 8 | 1
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
1.1 | Expand secondary transportation services offered by the airport | 2026-01-06 | 2026-12-06 | Manager | Secondary transportation system plan is developed and pitched to transportation system stakeholders | In Progress | On-time
| Task |  | Status | Results
| 1.1.1 Identify current transportation systems |  | 5%
| 1.1.2 Develop plan to include CCGA as a transportation stop |  | 0%
| 1.1.3 Approach transportation system stakeholders and pitch plan |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
1.2 | Identify new non-aviation revenue | 2025-07-31 | 2026-10-16 | Admin Team | Plan to secure new non-aviation revenue sources is developed and presented to the airport commission for action | In Progress | On-time
| Task |  | Status | Results
| 1.2.1 Develop list of potential non-aviation revenue sources |  | 100% | Advertising, additional land leases, terminal parking increased utilization
| 1.2.2 Identify target sources |  | 5%
| 1.2.3 Develop plan to secure target sources |  | 5%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
1.3 | Establish new airlines and routes | 2025-10-11 | 2026-11-09 | Manager | Marketing presentation pitched to at least 3 new air carriers | In Progress | On-time
| Task |  | Status | Results
| 1.3.1 Solicit main, discount, and regional carriers |  | 10% | Through JF, met with & present HYA to Avelo
| 1.3.2 Develop marketing presentation on CCGA potential as a desirable O&D airport |  | 15% | The Avelo presentation will serve as a template to build on
| 1.3.3 Pitch marketing presentation |  | 15% | Airline 1 10/14/2025 & Airline 2 engaged as of 11/13/25.
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
1.4 | Evaluate infrastructure to support four season aviation | 2025-08-11 | 2026-12-03 | Manager | Funding proposal is submitted to town of Barnstable | In Progress | On-time
| Task |  | Status | Results
| 1.4.1 Solicit architectural/engineering firm to assess present and future needs to develop terminal redesign options to include up to 3 jetways |  | 25% | Preliminary discussions w/ASG Aug 2025. Need planning firm to strategize & potential feasability study to base need. Imperative to identify funding sources due to declining Federal & State Grant Funding and possibility of CCGA not accepting Federal Grants indefinitely which may impact State willingness to provide CCGA w/grants.
| 1.4.2 Select preferred design |  | 10% | Advance terminal expansion and TSA screening area improvements to support increasing passenger demand, enhance security screening capacity, and improve customer service.
| 1.4.3 Submit funding proposal to town |  | 0%
| 1.4.4 Evaluate CCGA cold weather operations |  | 0%
Formulas:
O-NS = IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 2
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 3 | 1 | 4 | 0 | No
[8 empty] | T-NS | T-IP | T-C | 1 | 0
GOAL 2: | Involve & Engage Community Stakeholders and Neighbors (Residents) & Improve Collaboration | [6 empty] | 0 | 4 | 8
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
2.1 | Develop a neighborhood (residents) and business work group that meets regularly with airport management | 2025-12-03 | 2026-12-04 | Assistant Manager | Work group participants are established, and meetings are scheduled | Completed | On-time
| Task |  | Status | Results
| 2.1.1 Identify potential neighborhood and business interests |  | 100% | Potential intrests identifed
| 2.1.2 Solicit participation in work group |  | 100% | Community leaders
| 2.1.3 Set work group schedule for the year |  | 100% | Meeting Montly / Quartley as to meet public Facilitate monthly and quarterly meetings with stakeholders and the public to gather feedback, improve communication, and address community needs
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
2.2 | Enhance communications using a variety of media (print/non-print) | 2026-01-14 | 2026-11-25 | Assistant Manager | Plan using a variety of print/non-print media sources has been implemented | In Progress | On-time
| Task |  | Status | Results
| 2.2.1 Identify communication sources not in use |  | 100% | Use X, Instagram, Facebook, Print, Radio
| 2.2.2 Select which sources are a good fit to enhance communications |  | 90% | Created and initiated advertising and marketing efforts to enhance the visibility of Cape Cod Gateway Airport and support passenger growth.
| 2.2.3 Develop and implement communications plan |  | 75% | A comprehensive advertising campaign is scheduled to launch over the next several months utilizing multiple media channels to enhance the airport's visibility and outreach efforts.
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
2.3 | Develop new methods to communicate and solicit feedback | 2026-01-07 | 2027-01-07 | Assistant Manager | New feedback mechanism plan is implemented | In Progress | On-time
| Task |  | Status | Results
| 2.3.1 Identify new feedback mechanisms and their target market |  | 100% | Roundtable, Email Portal, Community Roundtable
| 2.3.2 Select preferred mechanism and develop implementation plan |  | 100% | Email Portal, open meeting questions
| 2.3.3 Implement new feedback mechanism plan |  | 75% | The IT Department and Airport Administration are collaborating to create and launch an email communication portal to enhance community outreach, improve stakeholder engagement, and gather public feedback.
| Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
2.4 | Establish community liaisons for interest groups | 2026-01-02 | 2026-11-25 | Assistant Manager | Liaisons have been assigned and outreach efforts underway | In Progress | On-time
| Task |  | Status | Results
| 2.4.1 Identify interest groups |  | 100% | PFAS, Noise, Schools
| 2.4.2 Assign liaisons for each group |  | 100% | liaisons established
| 2.4.3 Develop and implement outreach efforts |  | 85% | Pre-Planning Roundtables established, Town meetings
Formulas:
O-NS = IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 3
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 3 | 0 | 3 | 0 | No
[7 empty] | T-NS | T-IP | T-C |  | 1 | 0
GOAL 3: | Improve Regional Transportation Network | [5 empty] | 7 | 3 | 0
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
3.1 | Explore micro transit system to and from downtown Hyannis | 2026-02-12 | 2027-02-12 | Assistant Manager | A viable model of a micro transit system is developed and presented to the airport commission for action | In Progress | On-time
| Task |  | Status | Results
| 3.1.1 Identify viable micro transit modes |  | 5% | In Progress
| 3.1.2 Identify route map with stops |  | 0%
| 3.1.3 Develop micro transit system model |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
3.2 | Identify and evaluate similar regional transportation systems in US | 2026-02-12 | 2027-02-12 | Assistant Manager | A proposed model of a transportation network is developed and presented to the airport commission for action | In Progress | On-time
| Task |  | Status | Results
| 3.2.1 Identify airports similar to CCGA |  | 50% | EWB, MLB, SAV, PNS
| 3.2.2 Research transportation networks at identified airports |  | 0%
| 3.2.3 Develop model of transportation network proposed for CCGA |  | 0%
| 3.2.4 Incorporate feedback and present to ACUASI Director for approval |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
3.3 | Support the conduct of a regional transportation study | 2026-02-12 | 2027-02-12 | Assistant Manager | Study findings are presented to airport commission and town of Barnstable | In Progress | On-time
| Task |  | Status | Results
| 3.3.1 Elicit study sponsors (FAA, MASS DOT, Congress etc) |  | 5%
| 3.3.2 Facilitate and contribute to study |  | 0%
| 3.3.3 Present study findings to airport commission and town of Barnstable |  | 0%
Formulas:
O-NS = IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 4
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 3 | 2 | 5 | 0 | No
[7 empty] | T-NS | T-IP | T-C |  | 1 | 0
GOAL 4: | Enhance Aviation Education Opportunities | [5 empty] | 0 | 7 | 8
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
4.1 | Solicit Cape Cod Community College (CCCC) for aviation maintenance training facility | 2026-01-15 | 2026-12-31 | Assistant Manager | Pitch for aviation maintenance training facility is made to appropriate party at CCCC | In Progress | On-time
| Task |  | Status | Results
| 4.1.1 Identify appropriate party at CCCC to solicit |  | 20% | Working with College to develop Aviation Education Program.
| 4.1.2 Develop proposal for aviation maintenance training facility |  | 10% | Talking to college and airport tenants about maintenance program.
| 4.1.3 Pitch proposal to appropriate party |  | 5% | Researching appropriate partnerships.
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
4.2 | Solicit Career Day involvement from different schools | 2026-01-15 | 2026-12-31 | Assistant Manager | Targeted schools have agreed to participate in Career Day | Completed | On-time
| Task |  | Status | Results
| 4.2.1 Identify schools to target for participation |  | 100% | School Identified
| 4.2.2 Develop Career Day schedule for participation |  | 100% | Career day, conduct when offered.
| 4.2.3 Secure participation agreement from targeted schools |  | 100% | Participation Secured
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
4.3 | Solicit Career Day involvement from different speakers | 2026-01-15 | 2026-12-31 | Assistant Manager | Targeted speakers have agreed to participate in Career Day | Completed | On-time
| Task |  | Status | Results
| 4.3.1 Identify speakers to target for participation |  | 100% | Speakers Identified
| 4.3.2 Develop Career Day schedule for participation |  | 100% | Career day Participate when offered
| 4.3.3 Secure participation agreement from targeted schools |  | 100% | Secured Participation
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
4.4 | Implement yearly aviation education programs in local schools | 2025-01-15 | 2026-12-31 | Assistant Manager | Proposed aviation education programs are presented to targeted schools | In Progress | On-time
| Task |  | Status | Results
| 4.4.1 Identify schools to target for education programs |  | 100% | School Identified
| 4.4.2 Coordinate with FAA Aviation Education Counselor at New England Regional Office and other aviation organizations to develop programs |  | 50% | Working with New England Regional FAA
| 4.4.3 Present proposed programs to targeted schools |  | 25% | establishing school course at schools and Airport
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
4.5 | Enhance High School Intern Program | 2026-01-15 | 2026-12-31 | Assistant Manager | Enhanced High School Intern Program is presented to airport commission | In Progress | On-time
| Task |  | Status | Results
| 4.5.1 Survey/interview past high school interns for recommendations on how to enhance the program |  | 100% | Engaged with this year's interns to discuss their experiences and collect recommendations for enhancing and improving the internship program
| 4.5.2 Solicit aviation businesses at CCGA to participate in intern program |  | 75% | Fostered partnerships with airport tenants and business stakeholders to support the growth and long-term success of the Airport Internship Program
| 4.5.3 Develop enhanced intern program and present to airport commission |  | 50% | Designed internship placements and experiences to align with each intern's professional interests and objectives, ensuring meaningful and personalized development opportunities.
Formulas:
O-NS = IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 5
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 1 | 2 | 3 | 0 | No
[7 empty] | T-NS | T-IP | T-C |  | 1 | 0
GOAL 5: | Identify and Address Environmental Issues | [5 empty] | 2 | 1 | 6
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
5.1 | Educate pilot community and future air service stakeholders on recommended noise abatement procedures | 2026-01-15 | 2026-12-31 | Assistant Manager | Quarterly noise complaint reporting includes analysis of efficacy of marketing campaign and improvements related to it | Completed | On-time
| Task |  | Status | Results
| 5.1.1 Review existing noise abatement procedures for enhancements |  | 100% | Review current and past data
| 5.1.2 Develop noise abatement procedure marketing campaign that includes future air service stakeholders |  | 100% | Had Noise round table on September 16th @ BHS, more meetings to come.
| 5.1.3 Monitor noise complaints for improvement over 2024 |  | 100% | Have implemented Plane Noise
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
5.2 | Reduce emissions from 2025 baseline | 2026-02-12 | 2027-02-12 | Assistant Manager | Emission reduction plan is implemented, 10% emission reduction achieved in 2026 | In Progress | On-time
| Task |  | Status | Results
| 5.2.1 Establish emissions baseline for 2025 |  | 5%
| 5.2.2 Develop proposed emission reduction plan |  | 0%
| 5.2.3 Implement plan and monitor results |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
5.3 | Avoid chemical impact on ground water and environment through use of proper products | 2026-01-12 | 2027-02-12 | Assistant Manager | New environmentally safer chemical products are identified and transitioned to | Completed | On-time
| Task |  | Status | Results
| 5.3.1 Survey chemicals in use at CCGA |  | 100% | Have Safety Data Sheets on all chemicals
| 5.3.2 Identify alternative applications |  | 100% | Using green commeicals, including green hydralic fluid and F3 Foam
| 5.3.3 Transition to new products |  | 100% | F3 foam will be put in the ARFF Trucks in the next few months
Formulas:
O-NS = IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 6
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 5 | 0 | 5 | 0 | No
[7 empty] | T-NS | T-IP | T-C |  | 1 | 0
GOAL 6: | Promote, Engage & Implement New and Emerging Technology in Air Transportation, Safety & Noise Abatement | [5 empty] | 5 | 13 | 1
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
6.1 | Develop an Incubation Center for new technology | 2026-02-12 | 2027-02-12 | TBD | Incubation Center model for CCGA is presented to airport commission | In Progress | On-time
| Task |  | Status | Results
| 6.1.1 Research incubation center modelling |  | 5%
| 6.1.2 Select proposed model for CCGA |  | 0%
| 6.1.3 Present model to airport commission for action |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
6.2 | Entice tech companies for future self sufficiency | 2026-01-01 | 2026-12-31 | Assistant Manager | Proposals are presented to airport commission for action | In Progress | On-time
| Task |  | Status | Results
| 6.2.1 Identify services that could be replaced by self-sufficient tech |  | 100% | Fueling, Noise, Flight Tracking, Security
| 6.2.2 Solicit proposals from tech companies |  | 50% | Beta Testing
| 6.2.3 Present proposals to airport commission for action |  | 25% | Successfully implemented and launched the PlaneNoise software system.
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
6.3 | Develop and implement an Airport App for ease of parking, checking in, and all airport services | 2026-02-12 | 2027-02-12 | Assistant Manager | Airport App prototype is developed and presented to airport commission for approval | In Progress | On-time
| Task |  | Status | Results
| 6.3.1 Develop list of potential development sources (schools, existing apps, development contracts, etc) |  | 10%
| 6.3.2 Determine best source to meet objectives balancing efficiency and cost |  | 0%
| 6.3.3 Contract with best source |  | 0%
| 6.3.4 Present prototype to airport commission for approval |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
6.4 | Support electric aircraft including eVOTLs | 2026-02-12 | 2026-12-31 | Assistant Manager | Electric aircraft including eVOTLs are conducting recurring operations at CCGA | In Progress | On-time
| Task |  | Status | Results
| 6.4.1 Develop a project plan |  | 50% | Developed a proposal for the installation of electric vehicle charging stations at the airport to support sustainability initiatives and improve passenger services.
| 6.4.2 Identify infrastructure requirements |  | 25% | Identified power grid requirements to support planned infrastructure improvements and ensure reliable electrical capacity.
| 6.4.3 Determine charging station locations |  | 25% | Proposed two potential locations for power station installations to support airport infrastructure and operational needs.
| 6.4.4. Implement infrastructure changes |  | 10% | In-progress
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
6.5 | Identify new technology readily available in air transportation | 2026-02-12 | 2026-11-25 | Assistant Manager | At least one new air transportation technology has been identified and implemented | In Progress | On-time
| Task |  | Status | Results
| 6.5.1 Establish viability of new technology |  | 75% | Implemented PlaneNoise Software, testing fueling software with JetBlue
| 6.5.2 Investigate/evaluate how to utilize new technology |  | 50% | Noise and fueling tracking
| 6.5.3 Select new technology for implementation |  | 50% | Conducting testing in coordination with airline partners to ensure operational readiness and system performance.
| 6.5.4 Develop implementation plan for new technology |  | 20% | BETA Testing
| 6.5.5 Implement new technology according to plan |  | 20% | In progress
Formulas:
O-NS = IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 7
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 3 | 0 | 3 | 0 | No
[7 empty] | T-NS | T-IP | T-C |  | 1 | 0
GOAL 7: | Increase Annual Airport Operations | [5 empty] | 5 | 2 | 2
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
7.1 | Increase passenger traffic by expanding direct flight offerings | 2026-02-12 | 2026-11-25 | Assistant Manager | Passenger traffic is increased by at least 50% over 2024 | In Progress | On-time
| Task |  | Status | Results
| 7.1.1 Develop marketing pitch to present to main and discount carriers |  | 100% | Met with new airlines
| 7.1.2 Pitch marketing campaign to existing carriers for service into/out of CCGA |  | 0%
| 7.1.3 Provide incentives to secure deal |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
7.2 | Establish new airlines and routes | 2026-01-05 | 2027-06-10 | Assistant Manager | At least two new routes and 1 new airline are added in 2025 | In Progress | On-time
| Task |  | Status | Results
| 7.2.1 Develop marketing pitch to present new service main and discount carriers |  | 100% | Met with Air Carriers
| 7.2.2 Pitch marketing campaign to new carriers for service into/out of CCGA |  | 25%
| 7.2.3 Provide incentives to secure deal |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
7.3 | Increase general aviation operations | 2026-02-12 | 2027-02-12 | Assistant Manager | Increase GA operations over 2024 by at least 15% | In Progress | On-time
| Task |  | Status | Results
| 7.3.1 Develop quarterly “fly-in” events to entice GA pilots to HYA |  | 25% | Wings and wheels event
| 7.3.2 Develop marketing campaign to advertise HYA to NE GA community |  | 0%
| 7.3.3 Work with FAA Boston Consolidated TRACON to inform desire to use HYA for practice IFR approaches |  | 0%
Formulas:
O-NS = IF(AND([Target Start Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))

## Goal 8
| DASHBOARD | [5 empty] | O-NS | O-IP | O-C | On-time | Late | G-C (Y/N)
[7 empty] | 0 | 3 | 0 | 3 | 0 | No
[7 empty] | T-NS | T-IP | T-C |  | 1 | 0
GOAL 8: | Evaluate and Enhance Jet Fuel Purchase Programs | [5 empty] | 5 | 5 | 0
Status = Not Started, In Progress, Complete
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria | Obj. Status | Progress
8.1 | Evaluate existing program for providing jet fuel | 2026-01-15 | 2026-11-25 | Assistant Manager | Jet fuel program improvement plan is presented to airport commission for action | In Progress | On-time
| Task |  | Status | Results
| 8.1.1 Compare existing jet fuel program to other sellers in Northeast US |  | 50% | Looking at software and testing
| 8.1.2 Identify improvement in process and price |  | 50% | Waiting on proposal
| 8.1.3 Develop improvement plan to present to airport commission for action |  | 20% | In progress
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
8.2 | Develop and solicit jet fuel customer service survey | 2026-02-12 | 2027-02-12 | Assistant Manager | Achieve 30% improvement in customer service survey results in repeated survey | In Progress | On-time
| Task |  | Status | Results
| 8.2.1 Analyze survey results |  | 25% | Met with with vendore X-1 FBO
| 8.2.2 Develop action items to address survey issues |  | 0%
| 8.2.3 Repeat survey in 6 to 9 months to evaluate improvement |  | 0%
| 8.2.4 Develop messaging product |  | 0%
# | Objective | Target Start Date | Target Finish Date | Lead Resource | Success Criteria
8.3 | Perform data capture of fuel service event cycle | 2026-02-12 | 2027-02-12 | Assistant Manager | Demonstrate a 30% gain in fuel service efficiency after 6 months | In Progress | On-time
| Task |  | Status | Results
| 8.3.1 Create service log that captures time of request and time of delivery completion |  | 10%
| 8.3.2 Brief staff and emphasize service improvement targets |  | 0%
| 8.3.3 Analyze results after 6 months of data capture |  | 0%
Formulas:
O-NS = IF(AND([Target Start Date]<TODAY(),[Obj. Status]="Not Started"),"Late",IF(AND([Target Finish Date]<TODAY(),[Obj. Status]="In Progress"),"Late","On-time"))